## Sheet1
Schedule
Date | Milestone | Main work | Target duration
2026-10-06 | M1 — Foundation & Networking | Repo structure, Terraform structure, provider, variables, VPC, 2 AZs, 6 subnets, IGW, NAT, route tables, SGs | 6–8 h
2026-10-07 | M2 — Docker, ECR & ECS Fargate | Dockerize app/sample service, ECR, ECS cluster, task definition, service, CloudWatch logs | 6–8 h
2026-10-08 | M3 — ALB, Multi-AZ & Auto Scaling | ALB, target groups, health checks, 2-AZ Fargate tasks, scaling rules | 6–7 h
2026-10-09 | M4 — Automated Daily Deployment | Deploy script / CI pipeline, Terraform apply, Docker build, ECR push, ECS deploy, health check | 7–8 h
10–11 Oct | M5 — Database & Storage | Aurora/RDS, Redis, S3, EFS, Secrets Manager, KMS, DB connectivity | 10–12 h total
2026-10-12 | M6 — Edge, DNS & Authentication | Route 53, ACM, CloudFront, WAF, Cognito, HTTPS | 6–8 h
13–14 Oct | M7 — Serverless & Event Driven | API Gateway, Lambda, SQS, SNS, EventBridge, Step Functions, one real workflow | 10–12 h total
15–16 Oct | M8 — RAG Knowledge Pipeline | S3 knowledge bucket, ingestion workflow, chunking, Bedrock KB, OpenSearch Serverless | 12–14 h total
17–18 Oct | M9 — Lina AI Tutor / RAG Runtime | Fargate API → RAG retrieval → Bedrock → response, optional Transcribe/Polly | 10–12 h total
19–20 Oct | M10 — Security, Monitoring, CI/CD & Final Integration | CloudWatch dashboard, alarms, CloudTrail, Config, GuardDuty/Inspector where available, quality gates, backup/cost controls | 12–14 h total
2026-10-21 | Testing & failure scenarios | clean redeploy, task failure, auto scaling, alarms, RAG tests, full end-to-end validation | 6–8 h
2026-10-22 | Documentation & submission package | README, diagrams, screenshots, cost section, architecture explanation, known limitations, final GitHub cleanup | 6–8 h
2026-10-23 | Submission day | final smoke test, links, report/presentation, submit | 2–3 h